## Sheet1
# List of Tasks for First Scrum # | PIC | Status | Translate into Job story?(no need)
### Charging function ###
- Research how rechargeable batteries work and whether we can make a USB | Chong | To Do
charger built in so we don't have to remove the batteries |  |  | 12 | To Do
- Acquire batteries | Chong | Done | 21 | Done
- Acquire female mini-USB connector |  | To Do | 33
- Design or acquire charging circuit schematic |  | To Do | 0.63636
- Assemble charging circuit |  | To Do
### Brake light switch and cable ### | Manya, Stephen
- Research what kind of switch to use to actuate light | Manya
* Easy to press with a finger |  | Done
* Goes on when pressed, off when released |  | Done |  |  | Done
* (Possibly) has several settings (for future versions) |  | To Do |  |  | To Do
- Acquire switch |  | Done |  |  | Doing
- Design or acquire switch schematic |  | Done
- Research what kind of cable we need to connect switch to helmet | Stephen | Done
* Flexible
* Durable
* Protected from short-circuits (no exposed wires)
- Determine length of cable needed for a typical situation | 4.5 feet | Done
- Acquire cable |  | Done
### Brake light (first prototype: off-the-shelf solution from Planet Bike) ### | Manya, Stephen
- Figure out how the light works |  | Done
- Figure out how to incorporate recharging into the circuit (see Charging above) |  | To Do
- Find out how to make the handlebar switch work with the circuit inside the |  | Done
light (the current switch is a button-toggle with 3 settings: off, solid on,
and flash)
- Acquire any electronic components needed |  | To Do
- Assemble the circuit |  | To Do
- Design or acquire circuit schematic |  | Done
### Location tracker app ### | Dery
- Develop initial fow chartfor product development |  | Done
- Prioritize by function: bluetooth, gps and data log for history |  | Done
* Bluetooth connection (wireless)
- Find information about several wireframe softwares |  | Done
- Make a wireframe illustrating basic functionality |  | To Do
- Design a bluetooth diagram and find the component/sensor (microcontroller) |  | To Do
* Gps system for next scrum
To Do
### Handlebar attachment ### | Peng
- Determine 3 methods for attaching switch to handlebars |  | Done
* Weatherproof
* Easy to remove
- Decide which method is best for first prototype (possibly with input from |  | Done
users)
- Acquire or create handlebars for testing |  | Done
- Implement that method |  | Done
### Helmet attachment ### | Robert
- Determine 3 methods for attaching light to helmet |  | Done
- Decide which method is best for first prototype (possibly with input from users) |  | Done
- Acquire or create a helmet for testing |  | Done
- Implement that method |  | To Do