## Sheet1
No. | Task Content | Status | Who? | Target Scrum
Project Status
All | Communication | Doing
To Do
EE | Stephen, Manya, Dery |  |  |  |  | Done
| Perform an Electical wireless system that could use buttons to controll the LED. | Doing |  |  |  | Doing
1 | Test the initial components work or not. | Done | Manya | 3 |  | Cancelled
2 | Set up the XBee radio. | Done | Manya | 3
3 | Test Arduino chip | Done | Stephen | 3
4 | Test Xbee transmitter & receiver | Done |  | 3
5 | Create a schematic for the transmitter circuit part. | Done | Stephen, Manya, Dery | 3
6 | Create a schematic for the receiver circuit part. | Done | Stephen, Manya, Dery | 3
7 | Receive breakout board, headers, and sockets | Done | Stephen | 3 | 15
8 | Solder headers and sockets to breakout board | Done | Manya | 3
9 | Program Xbee radios to duplicate inputs | Doing | Manya | 4
10 | Connect Xbee transmitter to sensors/switches | Doing |  | 4
11 | Connect XBee receiver to Arduino | Doing |  | 4
12 | Write Arduino code to control lights | Done |  | 3
13 | Test Arduino code | Done |  | 3
14 | Test final circuit | Doing |  | 4
15 | Create demonstration video version 1 | Done |  | 3
16 | Ask for customer feedback (at least 3 bikers) | Done |  | 3
17 | Plan for how to miniaturize electrical components | To Do |  | 5
18 | Integration Testing. | Doing |  | 4
19 | Ask for customer feedback again (at least 3 bikers) | To Do |  | 4
20 | Document the testing precedure. | Doing |  | 4
21 | Create demonstration video version 2 |  |  | 4
| Solve Xbee line-pass diffuculties | To Do | Manya Dery Stephen | 4
Put project into enclosure for integration with mechanical parts
ME | Chong, Robert, Peng
1 | Create CAD design of the handlebar part | Doing
2
3 | Go Tinker Lab and EPIC
4 | Attachment mechanism between lights and helmets | Doing | Robert, Peng, Chong
5 | Talk to customer | Done | Robert | 3
6 | Draw CAD design for light | Done | Chong, Robert, Peng | 3
7 | Determine what materials to use | Doing | Chong, Robert, Peng | 4
8 | Create CAD design of the helmet part | Done | Robert, Chong, Peng | 3
9
10
11
12
13
14
15
16
17
18
19
General
### Charging function ###
| - Research how rechargeable batteries work and whether we can make a USB | To Do | Chong
charger built in so we don't have to remove the batteries
| - Acquire batteries | Done | Chong
| - Acquire female mini-USB connector | To Do
| - Design or acquire charging circuit schematic | To Do
| - Assemble charging circuit | To Do
| ### Brake light switch and cable ### |  | Manya, Stephen
| - Research what kind of switch to use to actuate light |  | Manya
| * Easy to press with a finger | Done
| * Goes on when pressed, off when released | Done
| * (Possibly) has several settings (for future versions) | Cancelled
| - Acquire switch | Done
| - Design or acquire switch schematic | Done
| - Research what kind of cable we need to connect switch to helmet | Done | Stephen
* Flexible
* Durable
* Protected from short-circuits (no exposed wires)
| - Determine length of cable needed for a typical situation | Done | 4.5 feet
| - Acquire cable | Done
| ### Brake light (first prototype: off-the-shelf solution from Planet Bike) ### |  | Manya, Stephen
| - Figure out how the light works | Done
| - Figure out how to incorporate recharging into the circuit (see Charging above) | Deferred
| - Find out how to make the handlebar switch work with the circuit inside the | Done
light (the current switch is a button-toggle with 3 settings: off, solid on,
and flash)
| - Acquire any electronic components needed | Done
| - Assemble the circuit | Done
| - Design or acquire circuit schematic | Done
| ### Location tracker app ### |  | Dery
| - Develop initial fow chartfor product development | Done
| - Prioritize by function: bluetooth, gps and data log for history | Done
* Bluetooth connection (wireless)
| - Find information about several wireframe softwares | Done
| - Make a wireframe illustrating basic functionality | Deferred
| - Design a bluetooth diagram and find the component/sensor (microcontroller) | Cancelled
| * Gps system for next scrum | Deferred
| ### Handlebar attachment ### |  | Peng
| - Determine 3 methods for attaching switch to handlebars | Done
* Weatherproof
* Easy to remove
| - Decide which method is best for first prototype (possibly with input from | Done
users)
| - Acquire or create handlebars for testing | Done
| - Implement that method | Done
| ### Helmet attachment ### |  | Robert
| - Determine 3 methods for attaching light to helmet | Done
| - Decide which method is best for first prototype (possibly with input from users) | Done
| - Acquire or create a helmet for testing | Done
| - Implement that method | Done
|  |  | Done | 39
|  |  | To Do | 7
|  |  | Doing | 11
|  |  | Deferred | 3
|  |  | Cancelled | 2
62